## Avg Demand Scenario
Domestic supply chain scenario
Assumptions | Port/facility overlap |  |  | 0.25 | (Percent of facility construction that can be done while port construction still underway
| Announcement date |  |  | 2024 | (New facilities have to be annoucned by end of 2023)
| Floating date adder |  |  | 1 | years
| Port upgrade duration |  |  | 4 | years
| Floating port upgrade adder |  |  | 1 | years
|  |  |  | Location |  |  | Timeline
Component | Factory | Type | Name | Port | State | Region | Announcement date | Port upgrade duration (yrs) | Facility construction (yrs) | Port/facility overlap (%) | Operational date | Duration | Port upgrade cost | Production capacity | Facility cost | Notes
Blade | SGRE | Announced | Portsmouth Marine Terminal, VA | Portsmouth Marine Terminal | VA | South Atlantic | 2021 | 4 | 5 | 0.25 | 2028 | 7 | 150 | 225 | 200
Blade | Blade 1 | Scenario | Port of Wilmington, NC | General Cargo Terminal at Port of Wilmington | NC | South Atlantic | 2024 | 4 | 5 | 0.25 | 2031 | 7 | 150 | 225 | 250 | Space and low cost
Blade | Blade 2 | Scenario | Mystic River, MA | Mystic River, Everett | MA | North Atlantic | 2024 | 4 | 5 | 0.25 | 2031 | 7 | 250 | 225 | 250 | Space and low cost
Blade | Blade 3 | Scenario | New Jersey Wind Port, NJ | New Jersey Wind Port | NJ | Central Atlantic | 2024 | 4 | 5 | 0.25 | 2031 | 7 | 150 | 225 | 250 | NJWP trying to attract blade facility. 4 year upgrade time to get to NJWP Phase 2 plus site prep
Blade | Blade 4 | Scenario | Coos Bay, OR | TBD - Coos Bay | OR | West Coast | 2025 | 5 | 5 | 0.25 | 2033 | 8 | 50 | 225 | 250
Nacelle | GE | Announced | New Jersey Wind Port, NJ | New Jersey Wind Port | NJ | Central Atlantic | 2021 | 4 | 5 | 0.33333 | 2028 | 7 | 150 | 100 | 250 | Override port/facility overlap
Nacelle | Vestas | Announced | New Jersey Wind Port, NJ | New Jersey Wind Port | NJ | Central Atlantic | 2021 | 4 | 5 | 0.33333 | 2028 | 7 | 150 | 100 | 250 | Override port/facility overlap
Nacelle | Nacelle 1 | Scenario | South Quay, RI | South Quay | RI | North Atlantic | 2024 | 4 | 5 | 0.25 | 2031 | 7 | 300 | 100 | 250
Nacelle | Nacelle 2 | Scenario | Port of Humboldt, CA | TBD - Humboldt | CA | West Coast | 2023 | 5 | 5 | 0.25 | 2031 | 8 | 50 | 100 | 250
Tower | Marmen Welcon | Announced | Port of Albany, NY | Port of Albany | NY | Central Atlantic | 2021 | 4 | 3 | 0.8 | 2025 | 4 | 250 | 150 | 300 | Check anticipated operational date. Override port/facilty overlap
Tower | Tower 1 | Scenario | Tradepoint Atlantic, MD | Tradepoint Atlantic | MD | South Atlantic | 2024 | 4 | 3 | 0.25 | 2030 | 6 | 150 | 100 | 250 | No air draft. Already has steel rolling plans
Tower | Tower 2 | Scenario | Searsport, ME | Searsport | ME | North Atlantic | 2024 | 4 | 3 | 0.25 | 2030 | 6 | 150 | 100 | 250 | No air draft. Towers could be used for floating
Tower | Tower 3 | Scenario | Port of Humboldt, CA | TBD - Humboldt | CA | West Coast | 2025 | 5 | 3 | 0.25 | 2032 | 7 | 150 | 100 | 250
Monopile | EEW | Announced | Port of Paulsboro, NJ | Port of Paulsboro | NJ | Central Atlantic | 2020 | 4 | 2 | 0.5 | 2025 | 5 | 150 | 100 | 400 | Check anticipated operational date
Monopile | US Wind | Announced | Tradepoint Atlantic, MD | Tradepoint Atlantic | MD | South Atlantic | 2021 | 4 | 3.5 | 0.25 | 2027 | 6 | 150 | 100 | 300 | Assumes port fab alrady done
Monopile | Monopile 1 | Scenario | Portsmouth Marine Terminal, VA | Portsmouth Marine Terminal | VA | South Atlantic | 2024 | 4 | 4 | 0.25 | 2031 | 7 | 150 | 100 | 410
Jacket | Jacket 1 | Scenario | Port of New Orleans, LA | Port of New Orleans | LA | Gulf of Mexico | 2024 | 4 | 2 | 0.25 | 2029 | 5 | 150 | 50 | 10 | Existing O&G expertise. Space. Assumes that operations can ramp up quickly
GBF | GBF 1 | Scenario | Radio Island, NC | Radio Island, Morehead City | NC | South Atlantic | 2025 | 2 | 2 | 0 | 2029 | 4 | 150 | 50 | 10 | Minimal port upgrades needed. Need wet sotrage space. Later announcement date due to lower TRL of GBF
Transition piece | Smulders | Announced | Port of Albany, NY | Port of Albany | NY | Central Atlantic | 2021 | 4 | 3 | 0.25 | 2027 | 6 | 50 | 100 | 200 | Check anticipated operational date
Transition piece | Transition piece 1 | Scenario | Port of Coeymans, NY | Port of Coeymans | NY | Central Atlantic | 2024 | 4 | 3 | 0.25 | 2030 | 6 | 300 | 100 | 300 | Steel rolling already at Port of Albany
Array cable | Hellenic | Announced | Tradepoint Atlantic, MD | Tradepoint Atlantic | MD | South Atlantic | 2021 | 4 | 6 | 0.25 | 2029 | 8 | 150 | 1000 | 200
Array cable | Array cable 1 | Scenario | Arthur Kill Terminal, NY | Arthur Kill Terminal | NY | Central Atlantic | 2024 | 4 | 6 | 0.25 | 2032 | 8 | 150 | 500 | 400 | AKT expected to be ready for operations in 2026
Export cable | Nexans | Announced | Goose Island, SC | Goose Island | SC | South Atlantic | 2018 | 4 | n/a | n/a | 2020 | 2 | 50 | 200 | 200 | Operational
Export cable | Prysmian | Announced | Brayton Point, MA | Brayton Point | MA | North Atlantic | 2021 | 4 | 6 | 0.25 | 2029 | 8 | 150 | 200 | 200
Export cable | Export cable 1 | Scenario | Quonset Business Park, RI | Quonset Business Park / Port of Davisville | RI | North Atlantic | 2024 | 4 | 6 | 0.25 | 2032 | 8 | 150 | 200 | 400 | Limited air draft - probably oK for cables
Export cable | Export cable 2 | Scenario | Port of Charlotte, SC | Columbus Terminal | SC | South Atlantic | 2024 | 4 | 6 | 0.25 | 2032 | 8 | 150 | 600 | 400 | HVDC
Steel plates | Nucor | Announced | Brandenburg, KY | Brandenburg | KY | South Atlantic | 2021 | 4 | 2 | 0.25 | 2026 | 5 | 150 | 60000 | 1000
Steel plates | Steel plate 1 | Scenario | Port of Brunswick, GA | Port of Brunswick | GA | South Atlantic | 2024 | 4 | 6 | 0.25 | 2032 | 8 | 150 | 1000000 | 2000
Casting | Casting 1 | Scenario | Inland facility, PA |  | PA | Other | 2024 | 0 | 3 | 0 | 2027 | 3 | 0 | 700 | 100 | Doesn't need to be at a port. Exising large foundries in OH, PA.
Flange | Flange 1 | Announced | Portsmouth, NH | Schiller Newington, Portsmouth | NH | North Atlantic | 2024 | 3 | 2 | 0.25 | 2028 | 4 | 200 | 5000 | 100 | USFR planned to be done in 2024
Semisubmersible | Semisubmersible 1 | Scenario | Port of Humboldt, CA | TBD - Humboldt | CA | West Coast | 2025 | 5 | 1 | 0.25 | 2030 | 5 | 150 | 50 | 100 | Assembly port
Semisubmersible | Semisubmersible 3 | Scenario | Coos Bay, OR | TBD - Coos Bay | OR | West Coast | 2025 | 5 | 1 | 0.25 | 2030 | 5 | 150 | 50 | 100 | Assembly port
Mooring chain | Mooring chain 1 | Scenario | TX port, TX | TBD - TX | TX | Gulf of Mexico | 2025 | 4 | 3 | 0.25 | 2031 | 6 | 150 | 2000 | 50 | Service WC and EC
Construction schedule:
[8 empty] | Row Labels | Count of Factory
[8 empty] | CA | 4
[8 empty] | GA | 1
[8 empty] | KY | 1
[8 empty] | LA | 3
[8 empty] | MA | 2
[8 empty] | MD | 3
[8 empty] | ME | 2
[8 empty] | NC | 2
[8 empty] | NH | 1
[8 empty] | NJ | 4
[8 empty] | NY | 4
[8 empty] | OR | 2
[8 empty] | PA | 1
[8 empty] | RI | 2
[8 empty] | SC | 2
[8 empty] | VA | 2
[8 empty] | WA | 1
[8 empty] | TX | 2
[8 empty] | Grand Total | 39