## Scenario
Domestic supply chain scenario
Assumptions | Port/facility overlap | 0.25 | (Percent of facility construction that can be done while port construction still underway
| Announcement date | 2023 | (New facilities have to be annoucned by end of 2023)
| Port upgrade duration | 3 | years
|  | Location |  |  | Timeline
Component | Factory | Port | State | Region | Announcement date | Port upgrade duration (yrs) | Facility construction (yrs) | Port/facility overlap (%) | Operational date | Duration | Notes
Blade | SGRE | Portsmouth Marine Terminal | VA | South Atlantic | 2021 | 3 | 3 | 0.25 | 2026 | 5
| Blade 1 | General Cargo Terminal at Port of Wilmington | NC | South Atlantic | 2023 | 3 | 3 | 0.25 | 2028 | 5 | Space and low cost
| Blade 2 | Newport News Marine Terminal | VA | South Atlantic | 2023 | 3 | 3 | 0.25 | 2028 | 5 | Space and low cost
| Blade 3 | New Jersey Wind Port | NJ | Central Atlantic | 2023 | 3 | 3 | 0.25 | 2028 | 5 | NJWP trying to attract blade facility. 4 year upgrade time to get to NJWP Phase 2 plus site prep
Nacelle | GE | New Jersey Wind Port | NJ | Central Atlantic | 2021 | 3 | 3 | 0.33333 | 2026 | 5 | Override port/facility overlap
| Vestas | New Jersey Wind Port | NJ | Central Atlantic | 2021 | 3 | 3 | 0.33333 | 2026 | 5 | Override port/facility overlap
| Nacelle 1 | South Quay | RI | North Atlantic | 2023 | 3 | 3 | 0.25 | 2028 | 5
Tower | Marmen Welcon | Port of Albany | NY | Central Atlantic | 2021 | 3 | 2.5 | 0.8 | 2024 | 3 | Check anticipated operational date. Override port/facilty overlap
| Tower 1 | Tradepoint Atlantic | MD | South Atlantic | 2023 | 3 | 2.5 | 0.25 | 2027 | 4 | No air draft. Already has steel rolling plans
| Tower 2 | Searsport | ME | North Atlantic | 2023 | 3 | 2.5 | 0.25 | 2027 | 4 | No air draft. Towers could be used for floating
Monopile | EEW | Port of Paulsboro | NJ | Central Atlantic | 2020 | 3 | 2 | 0.5 | 2024 | 4 | Check anticipated operational date
| US Wind | Tradepoint Atlantic | NJ | South Atlantic | 2021 | 3 | 3.5 | 0.25 | 2026 | 5 | Assumes port fab alrady done
Jacket | Jacket 1 | Port of New Orleans | LA | Gulf of Mexico | 2023 | 3 | 1 | 0.25 | 2026 | 3 | Existing O&G expertise. Space. Assumes that operations can ramp up quickly
GBF | GBF 1 | Radio Island, Morehead City | NC | South Atlantic | 2025 | 2 | 1 | 0 | 2028 | 3 | Minimal port upgrades needed. Need wet sotrage space. Later announcement date due to lower TRL of GBF
Transition piece | Smulders | Port of Albany | NY | Central Atlantic | 2021 | 3 | 2.5 | 0.25 | 2025 | 4 | Check anticipated operational date
| TP 1 | Port of Coeymans | NY | Central Atlantic | 2023 | 3 | 2.5 | 0.25 | 2027 | 4 | Steel rolling already at Port of Albany
Array cable | Hellenic | Tradepoint Atlantic | MD | South Atlantic | 2021 | 3 | 5 | 0.25 | 2027 | 6
| Array cable 1 | Arthur Kill Terminal | NY | Central Atlantic | 2023 | 3 | 5 | 0.25 | 2029 | 6 | AKT expected to be ready for operations in 2026
| Array cable 2 | Mystic River, Everett | MA | North Atlantic | 2023 | 3 | 5 | 0.25 | 2029 | 6
Export cable | Nexans | Goose Island | SC | South Atlantic | 2018 | 3 | n/a | n/a | 2020 | 2 | Operational
| Prysmian | Brayton Point | MA | North Atlantic | 2021 | 3 | 5 | 0.25 | 2027 | 6
| Export cable 1 | Quonset Business Park / Port of Davisville | RI | North Atlantic | 2023 | 3 | 5 | 0.25 | 2029 | 6 | Limited air draft - probably oK for cables
| Export cable 2 | Columbus Terminal | SC | South Atlantic | 2023 | 3 | 5 | 0.25 | 2029 | 6
Steel plates | Nucor | Brandenburg | KY | South Atlantic | 2021 | 3 | 2 | 0.25 | 2025 | 4
| Steel plate 1 | Port of Brunswick | GA | South Atlantic | 2023 | 3 | 5 | 0.25 | 2029 | 6
Construction schedule:
[6 empty] | Row Labels | Count of Factory
[6 empty] | GA | 1
[6 empty] | KY | 1
[6 empty] | LA | 1
[6 empty] | MA | 2
[6 empty] | MD | 2
[6 empty] | ME | 1
[6 empty] | NC | 2
[6 empty] | NJ | 5
[6 empty] | NY | 4
[6 empty] | RI | 2
[6 empty] | SC | 1
[6 empty] | VA | 2
[6 empty] | Grand Total | 24