## Avg Demand Scenario
Domestic supply chain scenario
Assumptions | Port/facility overlap |  | 0.25 | (Percent of facility construction that can be done while port construction still underway
| Announcement date |  | 2024 | (New facilities have to be annoucned by end of 2023)
| Floating date adder |  | 1 | years
| Port upgrade duration |  | 4 | years
| Floating port upgrade adder |  | 1 | years
|  |  | Location |  |  | Timeline
Component | Factory | Name | Port | State | Region | Announcement date | Port upgrade duration (yrs) | Facility construction (yrs) | Port/facility overlap (%) | Operational date | Duration | Notes
Blade | SGRE | Portsmouth Marine Terminal, VA | Portsmouth Marine Terminal | VA | South Atlantic | 2021 | 4 | 5 | 0.25 | 2028 | 7
| Blade 1 | Port of Wilmington, NC | General Cargo Terminal at Port of Wilmington | NC | South Atlantic | 2024 | 4 | 5 | 0.25 | 2031 | 7 | Space and low cost
| Blade 2 | Mystic River, MA | Mystic River, Everett | MA | North Atlantic | 2024 | 4 | 5 | 0.25 | 2031 | 7 | Space and low cost
| Blade 3 | New Jersey Wind Port, NJ | New Jersey Wind Port | NJ | Central Atlantic | 2024 | 4 | 5 | 0.25 | 2031 | 7 | NJWP trying to attract blade facility. 4 year upgrade time to get to NJWP Phase 2 plus site prep
| Blade 4 | Coos Bay, OR | TBD - Coos Bay | OR | West Coast | 2025 | 5 | 5 | 0.25 | 2033 | 8
Nacelle | GE | New Jersey Wind Port, NJ | New Jersey Wind Port | NJ | Central Atlantic | 2021 | 4 | 5 | 0.33333 | 2028 | 7 | Override port/facility overlap
| Vestas | New Jersey Wind Port, NJ | New Jersey Wind Port | NJ | Central Atlantic | 2021 | 4 | 5 | 0.33333 | 2028 | 7 | Override port/facility overlap
| Nacelle 1 | South Quay, RI | South Quay | RI | North Atlantic | 2024 | 4 | 5 | 0.25 | 2031 | 7
| Nacelle 2 | Port of Humboldt, CA | TBD - Humboldt | CA | West Coast | 2023 | 5 | 5 | 0.25 | 2031 | 8
Tower | Marmen Welcon | Port of Albany, NY | Port of Albany | NY | Central Atlantic | 2021 | 4 | 3 | 0.8 | 2025 | 4 | Check anticipated operational date. Override port/facilty overlap
| Tower 1 | Tradepoint Atlantic, MD | Tradepoint Atlantic | MD | South Atlantic | 2024 | 4 | 3 | 0.25 | 2030 | 6 | No air draft. Already has steel rolling plans
| Tower 2 | Searsport, ME | Searsport | ME | North Atlantic | 2024 | 4 | 3 | 0.25 | 2030 | 6 | No air draft. Towers could be used for floating
| Tower 3 | Port of Humboldt, CA | TBD - Humboldt | CA | West Coast | 2025 | 5 | 3 | 0.25 | 2032 | 7
Monopile | EEW | Port of Paulsboro, NJ | Port of Paulsboro | NJ | Central Atlantic | 2020 | 4 | 2 | 0.5 | 2025 | 5 | Check anticipated operational date
| US Wind | Tradepoint Atlantic, MD | Tradepoint Atlantic | MD | South Atlantic | 2021 | 4 | 3.5 | 0.25 | 2027 | 6 | Assumes port fab alrady done
Jacket | Jacket 1 | Port of New Orleans, LA | Port of New Orleans | LA | Gulf of Mexico | 2024 | 4 | 2 | 0.25 | 2029 | 5 | Existing O&G expertise. Space. Assumes that operations can ramp up quickly
GBF | GBF 1 | Radio Island, NC | Radio Island, Morehead City | NC | South Atlantic | 2025 | 2 | 2 | 0 | 2029 | 4 | Minimal port upgrades needed. Need wet sotrage space. Later announcement date due to lower TRL of GBF
Transition piece | Smulders | Port of Albany, NY | Port of Albany | NY | Central Atlantic | 2021 | 4 | 3 | 0.25 | 2027 | 6 | Check anticipated operational date
| Transition piece 1 | Port of Coeymans, NY | Port of Coeymans | NY | Central Atlantic | 2024 | 4 | 3 | 0.25 | 2030 | 6 | Steel rolling already at Port of Albany
Array cable | Hellenic | Tradepoint Atlantic, MD | Tradepoint Atlantic | MD | South Atlantic | 2021 | 4 | 6 | 0.25 | 2029 | 8
| Array cable 1 | Arthur Kill Terminal, NY | Arthur Kill Terminal | NY | Central Atlantic | 2024 | 4 | 6 | 0.25 | 2032 | 8 | AKT expected to be ready for operations in 2026
Export cable | Nexans | Goose Island, SC | Goose Island | SC | South Atlantic | 2018 | 4 | n/a | n/a | 2020 | 2 | Operational
| Prysmian | Brayton Point, MA | Brayton Point | MA | North Atlantic | 2021 | 4 | 6 | 0.25 | 2029 | 8
| Export cable 1 | Quonset Business Park, RI | Quonset Business Park / Port of Davisville | RI | North Atlantic | 2024 | 4 | 6 | 0.25 | 2032 | 8 | Limited air draft - probably oK for cables
| Export cable 2 | Port of Charlotte, SC | Columbus Terminal | SC | South Atlantic | 2024 | 4 | 6 | 0.25 | 2032 | 8
Steel plates | Nucor | Brandenburg, KY | Brandenburg | KY | South Atlantic | 2021 | 4 | 2 | 0.25 | 2026 | 5
| Steel plate 1 | Port of Brunswick, GA | Port of Brunswick | GA | South Atlantic | 2024 | 4 | 6 | 0.25 | 2032 | 8
Casting | Casting 1 | Inland facility, PA |  | PA | Other | 2024 | 0 | 3 | 0 | 2027 | 3 | Doesn't need to be at a port. Exising large foundries in OH, PA.
Flange | Flange 1 | Portsmouth, NH | Schiller Newington, Portsmouth | NH | North Atlantic | 2024 | 3 | 2 | 0.25 | 2028 | 4 | USFR planned to be done in 2024
Semisubmersible | Semisubmersible 1 | Port of Humboldt, CA | TBD - Humboldt | CA | West Coast | 2025 | 5 | 1 | 0.25 | 2030 | 5 | Assembly port
| Semisubmersible 2 | Central Coast, CA | TBD - Central Coast | CA | West Coast | 2025 | 5 | 1 | 0.25 | 2030 | 5 | Assembly port
| Semisubmersible 3 | Coos Bay, OR | TBD - Coos Bay | OR | West Coast | 2025 | 5 | 1 | 0.25 | 2030 | 5 | Assembly port
| Semisubmersible 4 | Port of New Orleans, LA | Port of New Orleans | LA | Gulf of Mexico | 2031 | 1 | 1 | 0.25 | 2032 | 1 | Assembly port
| Semisubmersible 5 | Portsmouth Marine Terminal, VA | Portsmouth Marine Terminal | VA | South Atlantic | 2030 | 1 | 1 | 0.25 | 2031 | 1 | Assembly port
| Semisubmersible 6 | Searsport, ME | Searsport | ME | North Atlantic | 2029 | 1 | 1 | 0.25 | 2030 | 1 | Assembly port
Stationkeeping | Mooring chain 1 | TX port, TX | TBD - TX | TX | Gulf of Mexico | 2025 | 4 | 3 | 0.25 | 2031 | 6 | Service WC and EC
| Mooring rope 1 | Port of New Orleans, LA | Port of New Orleans | LA | Gulf of Mexico | 2024 | 4 | 3 | 0.25 | 2030 | 6 | Service WC and EC
Construction schedule:
[7 empty] | Row Labels | Count of Factory
[7 empty] | CA | 4
[7 empty] | GA | 1
[7 empty] | KY | 1
[7 empty] | LA | 3
[7 empty] | MA | 2
[7 empty] | MD | 3
[7 empty] | ME | 2
[7 empty] | NC | 2
[7 empty] | NH | 1
[7 empty] | NJ | 4
[7 empty] | NY | 4
[7 empty] | OR | 2
[7 empty] | PA | 1
[7 empty] | RI | 2
[7 empty] | SC | 2
[7 empty] | VA | 2
[7 empty] | WA | 1
[7 empty] | TX | 2
[7 empty] | Grand Total | 39