## Scenario
Domestic supply chain scenario
Assumptions | Port/facility overlap | 0.25 | (Percent of facility construction that can be done while port construction still underway
| Announcement date | 2023 | (New facilities have to be annoucned by end of 2023)
| Port upgrade duration | 3 | years
|  | Location |  |  | Timeline
Component | Factory | Port | State | Region | Announcement date | Port upgrade duration (yrs) | Facility construction (yrs) | Port/facility overlap (%) | Operational date | Duration | Notes
Blade | SGRE | Portsmouth Marine Terminal | VA | South Atlantic | 2021 | 3 | 3 | 0.25 | 2026 | 5
| Blade 1 | General Cargo Terminal at Port of Wilmington | NC | South Atlantic | 2023 | 3 | 3 | 0.25 | 2028 | 5 | Space and low cost
| Blade 2 | Newport News Marine Terminal | VA | South Atlantic | 2023 | 3 | 3 | 0.25 | 2028 | 5 | Space and low cost
| Blade 3 | New Jersey Wind Port | NJ | Central Atlantic | 2023 | 3 | 3 | 0.25 | 2028 | 5 | NJWP trying to attract blade facility. 4 year upgrade time to get to NJWP Phase 2 plus site prep
Nacelle | GE | New Jersey Wind Port | NJ | Central Atlantic | 2021 | 3 | 3 | 0.33333 | 2026 | 5 | Override port/facility overlap
| Vestas | New Jersey Wind Port | NJ | Central Atlantic | 2021 | 3 | 3 | 0.33333 | 2026 | 5 | Override port/facility overlap
| Nacelle 1 | South Quay | RI | North Atlantic | 2023 | 3 | 3 | 0.25 | 2028 | 5
Tower | Marmen Welcon | Port of Albany | NY | Central Atlantic | 2021 | 3 | 2.5 | 0.8 | 2024 | 3 | Check anticipated operational date. Override port/facilty overlap
| Tower 1 | Tradepoint Atlantic | MD | South Atlantic | 2023 | 3 | 2.5 | 0.25 | 2027 | 4 | No air draft. Already has steel rolling plans
| Tower 2 | Searsport | ME | North Atlantic | 2023 | 3 | 2.5 | 0.25 | 2027 | 4 | No air draft. Towers could be used for floating
Monopile | EEW | Port of Paulsboro | NJ | Central Atlantic | 2020 | 3 | 2 | 0.5 | 2024 | 4 | Check anticipated operational date
| US Wind | Tradepoint Atlantic | NJ | South Atlantic | 2021 | 3 | 3.5 | 0.25 | 2026 | 5 | Assumes port fab alrady done
Jacket | Jacket 1 | Port of New Orleans | LA | Gulf of Mexico | 2023 | 3 | 1 | 0.25 | 2026 | 3 | Existing O&G expertise. Space. Assumes that operations can ramp up quickly
Transition piece | Smulders | Port of Albany | NY | Central Atlantic | 2021 | 3 | 2.5 | 0.25 | 2025 | 4 | Check anticipated operational date
| TP 1 | Port of Coeymans | NY | Central Atlantic | 2023 | 3 | 2.5 | 0.25 | 2027 | 4 | Steel rolling already at Port of Albany
Array cable | Hellenic | Tradepoint Atlantic | MD | South Atlantic | 2021 | 3 | 5 | 0.25 | 2027 | 6
| Array cable 1 | Arthur Kill Terminal | NY | Central Atlantic | 2023 | 3 | 5 | 0.25 | 2029 | 6 | AKT expected to be ready for operations in 2026
| Array cable 2 | Mystic River, Everett | MA | North Atlantic | 2023 | 3 | 5 | 0.25 | 2029 | 6
Export cable | Nexans | Goose Island | SC | South Atlantic | 2018 | 3 | n/a | n/a | 2020 | 2 | Operational
| Prysmian | Brayton Point | MA | North Atlantic | 2021 | 3 | 5 | 0.25 | 2027 | 6
| Export cable 1 | Quonset Business Park / Port of Davisville | RI | North Atlantic | 2023 | 3 | 5 | 0.25 | 2029 | 6 | Limited air draft - probably oK for cables
| Export cable 2 | Radio Island, Morehead City | NC | South Atlantic | 2023 | 3 | 5 | 0.25 | 2029 | 6
Steel plates | Nucor | Brandenburg | KY | South Atlantic | 2021 | 3 | 2 | 0.25 | 2025 | 4
| Steel plate 1 | Port of Brunswick | GA | South Atlantic | 2023 | 3 | 5 | 0.25 | 2029 | 6
Construction schedule:
[6 empty] | Row Labels | Count of Factory
[6 empty] | GA | 1
[6 empty] | KY | 1
[6 empty] | LA | 1
[6 empty] | MA | 2
[6 empty] | MD | 2
[6 empty] | ME | 1
[6 empty] | NC | 2
[6 empty] | NJ | 5
[6 empty] | NY | 4
[6 empty] | RI | 2
[6 empty] | SC | 1
[6 empty] | VA | 2
[6 empty] | Grand Total | 24

## Blade
Port | State | Region | Laydown area (acres) | Quayside length (m) | Berth depth (m) | Channel depth (m) | Bearing capacity (t/m2) | Air draft restriction (m) | State OSW goals | Existing commitments | Blade_decision | Blade_upgrade_cost | Blade_upgrade_time | Blade_fails
Port of Brunswick | GA | South Atlantic | 707 | 1876 | 10.5 | 10.5 | 0 | 62 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Sparrows Point / TradePoint Atlantic | MD | South Atlantic | 680 | 1020 | 11 | 11 | 0 | 999 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
Portsmouth Marine Terminal | VA | South Atlantic | 287 | 1079 | 13.1 | 13.1 | 0 | 999 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
General Cargo Terminal at Port of Wilmington | NC | South Atlantic | 284 | 2063 | 13 | 13 | 0 | 64 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Newport News Marine Terminal | VA | South Atlantic | 165 | 1060 | 12.2 | 12.2 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Columbus Terminal | SC | South Atlantic | 155 | 1066 | 13.7 | 13.7 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Lambert's Point, Norfolk | VA | South Atlantic | 110 | 517 | 14.6 | 12.2 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Brayton Point | MA | North Atlantic | 250 | 213 | 10.5 | 10.5 | 9.8 | 41.15 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
Quonset Business Park / Port of Davisville | RI | North Atlantic | 200 | 434 | 10.36 | 9.75 | 0 | 59.13 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
PG & E Facility, Bridgeport | CT | North Atlantic | 100 | 121.92 | 9.14 | 9 | 5.38 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Searsport | ME | North Atlantic | 80 | 488 | 12.2 | 10.67 | 5 | 999 | 0 | 0 | Yes | 250 | 3 | ['laydown area', 'bearing capacity']
Mystic River, Everett | MA | North Atlantic | 80 | 380 | 11.5 | 12.2 | 0 | 41.15 | 1 | 0 | Yes | 250 | 3 | ['laydown area', 'bearing capacity']
Boston Autoport | MA | North Atlantic | 80 | 335 | 12 | 10.67 | 9.8 | 41 | 1 | 0 | Yes | 250 | 3 | ['laydown area', 'bearing capacity']
New Bedford | MA | North Atlantic | 30 | 366 | 9.1 | 9.1 | 20 | 999 | 1 | 1 | Yes | 200 | 3 | ['laydown area']
Port Everglades | FL | GOM | 2190 | 2000 | 11 | 12.5 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Galveston | TX | GOM | 840 | 10229 | 7.1 | 11 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Pascagoula | MS | GOM | 747 | 3857 | 11 | 9.4 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of New Orleans | LA | GOM | 460 | 3400 | 11 | 11 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Beaumont | TX | GOM | 206 | 2575 | 11 | 11 | 0 | 41.5 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Palm Beach | FL | GOM | 162 | 1981 | 9.4 | 9.4 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Gulf Port | MS | GOM | 160 | 1219 | 9.4 | 9.4 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Tampa | FL | GOM | 100 | 1829 | 11 | 12.5 | 0 | 58.2 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
New York Container Terminal | NY | Central Atlantic | 260 | 650 | 13.7 | 15.24 | 0 | 46.9 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Albany | NY | Central Atlantic | 200 | 1798 | 9.14 | 9.14 | 5 | 40 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
Naval Weapons Station Earle Pier Complex, Belford | NJ | Central Atlantic | 200 | 215 | 13.7 | 10.67 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Paulsboro | NJ | Central Atlantic | 120 | 260 | 12.2 | 12.2 | 0 | 53 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
Werner Power Station | NJ | Central Atlantic | 90 | 250 | 7 | 7.62 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
South Brooklyn Marine Terminal | NY | Central Atlantic | 53 | 413 | 10.7 | 12.2 | 30 | 65.5 | 1 | 1 | Yes | 200 | 3 | ['laydown area']
Port of Coeymans Marine Terminal | NY | Central Atlantic | 50 | 1067 | 9.14 | 9.14 | 19.5 | 41 | 1 | 1 | Yes | 200 | 3 | ['laydown area']
Arthur Kill Terminal | NY | Central Atlantic | 32 | 396 | 10.67 | 10.67 | 29 | 999 | 1 | 0 | Yes | 200 | 3 | ['laydown area']

## Nacelle
Port | State | Region | Laydown area (acres) | Quayside length (m) | Berth depth (m) | Channel depth (m) | Bearing capacity (t/m2) | Air draft restriction (m) | State OSW goals | Existing commitments | Nacelle_decision | Nacelle_upgrade_cost | Nacelle_upgrade_time | Nacelle_fails
Port of Brunswick | GA | South Atlantic | 707 | 1876 | 10.5 | 10.5 | 0 | 62 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Sparrows Point / TradePoint Atlantic | MD | South Atlantic | 680 | 1020 | 11 | 11 | 0 | 999 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
Portsmouth Marine Terminal | VA | South Atlantic | 287 | 1079 | 13.1 | 13.1 | 0 | 999 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
General Cargo Terminal at Port of Wilmington | NC | South Atlantic | 284 | 2063 | 13 | 13 | 0 | 64 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Newport News Marine Terminal | VA | South Atlantic | 165 | 1060 | 12.2 | 12.2 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Columbus Terminal | SC | South Atlantic | 155 | 1066 | 13.7 | 13.7 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Lambert's Point, Norfolk | VA | South Atlantic | 110 | 517 | 14.6 | 12.2 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Quonset Business Park / Port of Davisville | RI | North Atlantic | 200 | 434 | 10.36 | 9.75 | 0 | 59.13 | 0 | 0 | Yes | 300 | 3 | ['quayside length', 'channel depth', 'bearing capacity']
Searsport | ME | North Atlantic | 80 | 488 | 12.2 | 10.67 | 5 | 999 | 0 | 0 | Yes | 200 | 3 | ['quayside length', 'bearing capacity']
Mystic River, Everett | MA | North Atlantic | 80 | 380 | 11.5 | 12.2 | 0 | 41.15 | 1 | 0 | Yes | 200 | 3 | ['quayside length', 'bearing capacity']
Prov Port | RI | North Atlantic | 50 | 1097 | 9.1 | 12.2 | 0 | 59.13 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
New London State Pier | CT | North Atlantic | 45 | 1244 | 12.2 | 10.7 | 0 | 999 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
Salem | MA | North Atlantic | 42 | 484 | 9.75 | 9.75 | 0 | 999 | 1 | 1 | Yes | 300 | 3 | ['quayside length', 'channel depth', 'bearing capacity']
South Quay | RI | North Atlantic | 35 | 457 | 10.36 | 12.2 | 0 | 59.13 | 0 | 0 | Yes | 300 | 3 | ['laydown area', 'quayside length', 'bearing capacity']
Port Everglades | FL | GOM | 2190 | 2000 | 11 | 12.5 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Galveston | TX | GOM | 840 | 10229 | 7.1 | 11 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Pascagoula | MS | GOM | 747 | 3857 | 11 | 9.4 | 0 | 999 | 0 | 0 | Yes | 250 | 3 | ['channel depth', 'bearing capacity']
Port of New Orleans | LA | GOM | 460 | 3400 | 11 | 11 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Beaumont | TX | GOM | 206 | 2575 | 11 | 11 | 0 | 41.5 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Palm Beach | FL | GOM | 162 | 1981 | 9.4 | 9.4 | 0 | 999 | 0 | 0 | Yes | 250 | 3 | ['channel depth', 'bearing capacity']
Port of Gulf Port | MS | GOM | 160 | 1219 | 9.4 | 9.4 | 0 | 999 | 0 | 0 | Yes | 250 | 3 | ['channel depth', 'bearing capacity']
Port of Tampa | FL | GOM | 100 | 1829 | 11 | 12.5 | 0 | 58.2 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
New York Container Terminal | NY | Central Atlantic | 260 | 650 | 13.7 | 15.24 | 0 | 46.9 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Albany | NY | Central Atlantic | 200 | 1798 | 9.14 | 9.14 | 5 | 40 | 1 | 1 | Yes | 250 | 3 | ['channel depth', 'bearing capacity']
South Brooklyn Marine Terminal | NY | Central Atlantic | 53 | 413 | 10.7 | 12.2 | 30 | 65.5 | 1 | 1 | Yes | 150 | 3 | ['quayside length']
Port of Coeymans Marine Terminal | NY | Central Atlantic | 50 | 1067 | 9.14 | 9.14 | 19.5 | 41 | 1 | 1 | Yes | 200 | 3 | ['channel depth']
Arthur Kill Terminal | NY | Central Atlantic | 32 | 396 | 10.67 | 10.67 | 29 | 999 | 1 | 0 | Yes | 250 | 3 | ['laydown area', 'quayside length']

## Tower
Port | State | Region | Laydown area (acres) | Quayside length (m) | Berth depth (m) | Channel depth (m) | Bearing capacity (t/m2) | Air draft restriction (m) | State OSW goals | Existing commitments | Tower_decision | Tower_upgrade_cost | Tower_upgrade_time | Tower_fails
Port of Brunswick | GA | South Atlantic | 707 | 1876 | 10.5 | 10.5 | 0 | 62 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Sparrows Point / TradePoint Atlantic | MD | South Atlantic | 680 | 1020 | 11 | 11 | 0 | 999 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
Portsmouth Marine Terminal | VA | South Atlantic | 287 | 1079 | 13.1 | 13.1 | 0 | 999 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
General Cargo Terminal at Port of Wilmington | NC | South Atlantic | 284 | 2063 | 13 | 13 | 0 | 64 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Newport News Marine Terminal | VA | South Atlantic | 165 | 1060 | 12.2 | 12.2 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Columbus Terminal | SC | South Atlantic | 155 | 1066 | 13.7 | 13.7 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Lambert's Point, Norfolk | VA | South Atlantic | 110 | 517 | 14.6 | 12.2 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Brayton Point | MA | North Atlantic | 250 | 213 | 10.5 | 10.5 | 9.8 | 41.15 | 1 | 1 | Yes | 100 | 3 | []
Quonset Business Park / Port of Davisville | RI | North Atlantic | 200 | 434 | 10.36 | 9.75 | 0 | 59.13 | 0 | 0 | Yes | 250 | 3 | ['channel depth', 'bearing capacity']
PG & E Facility, Bridgeport | CT | North Atlantic | 100 | 121.92 | 9.14 | 9 | 5.38 | 999 | 1 | 0 | Yes | 300 | 3 | ['quayside length', 'channel depth', 'bearing capacity']
Searsport | ME | North Atlantic | 80 | 488 | 12.2 | 10.67 | 5 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Mystic River, Everett | MA | North Atlantic | 80 | 380 | 11.5 | 12.2 | 0 | 41.15 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Boston Autoport | MA | North Atlantic | 80 | 335 | 12 | 10.67 | 9.8 | 41 | 1 | 0 | Yes | 100 | 3 | []
Prov Port | RI | North Atlantic | 50 | 1097 | 9.1 | 12.2 | 0 | 59.13 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
New London State Pier | CT | North Atlantic | 45 | 1244 | 12.2 | 10.7 | 0 | 999 | 1 | 1 | Yes | 250 | 3 | ['laydown area', 'bearing capacity']
Salem | MA | North Atlantic | 42 | 484 | 9.75 | 9.75 | 0 | 999 | 1 | 1 | Yes | 350 | 3 | ['laydown area', 'channel depth', 'bearing capacity']
South Quay | RI | North Atlantic | 35 | 457 | 10.36 | 12.2 | 0 | 59.13 | 0 | 0 | Yes | 250 | 3 | ['laydown area', 'bearing capacity']
New Bedford | MA | North Atlantic | 30 | 366 | 9.1 | 9.1 | 20 | 999 | 1 | 1 | Yes | 300 | 3 | ['laydown area', 'channel depth']
New Haven Terminal | CT | North Atlantic | 25 | 229 | 10.97 | 10.67 | 10.67 | 999 | 1 | 0 | Yes | 200 | 3 | ['laydown area']
Port Everglades | FL | GOM | 2190 | 2000 | 11 | 12.5 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Galveston | TX | GOM | 840 | 10229 | 7.1 | 11 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Pascagoula | MS | GOM | 747 | 3857 | 11 | 9.4 | 0 | 999 | 0 | 0 | Yes | 250 | 3 | ['channel depth', 'bearing capacity']
Port of New Orleans | LA | GOM | 460 | 3400 | 11 | 11 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Beaumont | TX | GOM | 206 | 2575 | 11 | 11 | 0 | 41.5 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Palm Beach | FL | GOM | 162 | 1981 | 9.4 | 9.4 | 0 | 999 | 0 | 0 | Yes | 250 | 3 | ['channel depth', 'bearing capacity']
Port of Gulf Port | MS | GOM | 160 | 1219 | 9.4 | 9.4 | 0 | 999 | 0 | 0 | Yes | 250 | 3 | ['channel depth', 'bearing capacity']
Port of Tampa | FL | GOM | 100 | 1829 | 11 | 12.5 | 0 | 58.2 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
New York Container Terminal | NY | Central Atlantic | 260 | 650 | 13.7 | 15.24 | 0 | 46.9 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Albany | NY | Central Atlantic | 200 | 1798 | 9.14 | 9.14 | 5 | 40 | 1 | 1 | Yes | 250 | 3 | ['channel depth', 'bearing capacity']
Naval Weapons Station Earle Pier Complex, Belford | NJ | Central Atlantic | 200 | 215 | 13.7 | 10.67 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Paulsboro | NJ | Central Atlantic | 120 | 260 | 12.2 | 12.2 | 0 | 53 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
Werner Power Station | NJ | Central Atlantic | 90 | 250 | 7 | 7.62 | 0 | 999 | 1 | 0 | Yes | 250 | 3 | ['channel depth', 'bearing capacity']
South Brooklyn Marine Terminal | NY | Central Atlantic | 53 | 413 | 10.7 | 12.2 | 30 | 65.5 | 1 | 1 | Yes | 100 | 3 | []
Port of Coeymans Marine Terminal | NY | Central Atlantic | 50 | 1067 | 9.14 | 9.14 | 19.5 | 41 | 1 | 1 | Yes | 200 | 3 | ['channel depth']
Arthur Kill Terminal | NY | Central Atlantic | 32 | 396 | 10.67 | 10.67 | 29 | 999 | 1 | 0 | Yes | 200 | 3 | ['laydown area']

## Monopile
Port | State | Region | Laydown area (acres) | Quayside length (m) | Berth depth (m) | Channel depth (m) | Bearing capacity (t/m2) | Air draft restriction (m) | State OSW goals | Existing commitments | Monopile_decision | Monopile_upgrade_cost | Monopile_upgrade_time | Monopile_fails
Port of Brunswick | GA | South Atlantic | 707 | 1876 | 10.5 | 10.5 | 0 | 62 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Sparrows Point / TradePoint Atlantic | MD | South Atlantic | 680 | 1020 | 11 | 11 | 0 | 999 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
Portsmouth Marine Terminal | VA | South Atlantic | 287 | 1079 | 13.1 | 13.1 | 0 | 999 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
General Cargo Terminal at Port of Wilmington | NC | South Atlantic | 284 | 2063 | 13 | 13 | 0 | 64 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Newport News Marine Terminal | VA | South Atlantic | 165 | 1060 | 12.2 | 12.2 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Columbus Terminal | SC | South Atlantic | 155 | 1066 | 13.7 | 13.7 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Lambert's Point, Norfolk | VA | South Atlantic | 110 | 517 | 14.6 | 12.2 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Brayton Point | MA | North Atlantic | 250 | 213 | 10.5 | 10.5 | 9.8 | 41.15 | 1 | 1 | Yes | 200 | 3 | ['quayside length', 'bearing capacity']
Quonset Business Park / Port of Davisville | RI | North Atlantic | 200 | 434 | 10.36 | 9.75 | 0 | 59.13 | 0 | 0 | Yes | 200 | 3 | ['quayside length', 'bearing capacity']
Searsport | ME | North Atlantic | 80 | 488 | 12.2 | 10.67 | 5 | 999 | 0 | 0 | Yes | 300 | 3 | ['laydown area', 'quayside length', 'bearing capacity']
Mystic River, Everett | MA | North Atlantic | 80 | 380 | 11.5 | 12.2 | 0 | 41.15 | 1 | 0 | Yes | 300 | 3 | ['laydown area', 'quayside length', 'bearing capacity']
Boston Autoport | MA | North Atlantic | 80 | 335 | 12 | 10.67 | 9.8 | 41 | 1 | 0 | Yes | 300 | 3 | ['laydown area', 'quayside length', 'bearing capacity']
Port Everglades | FL | GOM | 2190 | 2000 | 11 | 12.5 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Galveston | TX | GOM | 840 | 10229 | 7.1 | 11 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Pascagoula | MS | GOM | 747 | 3857 | 11 | 9.4 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of New Orleans | LA | GOM | 460 | 3400 | 11 | 11 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Beaumont | TX | GOM | 206 | 2575 | 11 | 11 | 0 | 41.5 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Palm Beach | FL | GOM | 162 | 1981 | 9.4 | 9.4 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Gulf Port | MS | GOM | 160 | 1219 | 9.4 | 9.4 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Tampa | FL | GOM | 100 | 1829 | 11 | 12.5 | 0 | 58.2 | 0 | 0 | Yes | 250 | 3 | ['laydown area', 'bearing capacity']
New York Container Terminal | NY | Central Atlantic | 260 | 650 | 13.7 | 15.24 | 0 | 46.9 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Albany | NY | Central Atlantic | 200 | 1798 | 9.14 | 9.14 | 5 | 40 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
South Brooklyn Marine Terminal | NY | Central Atlantic | 53 | 413 | 10.7 | 12.2 | 30 | 65.5 | 1 | 1 | Yes | 250 | 3 | ['laydown area', 'quayside length']
Port of Coeymans Marine Terminal | NY | Central Atlantic | 50 | 1067 | 9.14 | 9.14 | 19.5 | 41 | 1 | 1 | Yes | 200 | 3 | ['laydown area']
Arthur Kill Terminal | NY | Central Atlantic | 32 | 396 | 10.67 | 10.67 | 29 | 999 | 1 | 0 | Yes | 250 | 3 | ['laydown area', 'quayside length']

## Jacket
Port | State | Region | Laydown area (acres) | Quayside length (m) | Berth depth (m) | Channel depth (m) | Bearing capacity (t/m2) | Air draft restriction (m) | State OSW goals | Existing commitments | Jacket_decision | Jacket_upgrade_cost | Jacket_upgrade_time | Jacket_fails
Port of Brunswick | GA | South Atlantic | 707 | 1876 | 10.5 | 10.5 | 0 | 62 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Sparrows Point / TradePoint Atlantic | MD | South Atlantic | 680 | 1020 | 11 | 11 | 0 | 999 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
Portsmouth Marine Terminal | VA | South Atlantic | 287 | 1079 | 13.1 | 13.1 | 0 | 999 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
General Cargo Terminal at Port of Wilmington | NC | South Atlantic | 284 | 2063 | 13 | 13 | 0 | 64 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Newport News Marine Terminal | VA | South Atlantic | 165 | 1060 | 12.2 | 12.2 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Columbus Terminal | SC | South Atlantic | 155 | 1066 | 13.7 | 13.7 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Lambert's Point, Norfolk | VA | South Atlantic | 110 | 517 | 14.6 | 12.2 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
PG & E Facility, Bridgeport | CT | North Atlantic | 100 | 121.92 | 9.14 | 9 | 5.38 | 999 | 1 | 0 | Yes | 200 | 3 | ['quayside length', 'bearing capacity']
Searsport | ME | North Atlantic | 80 | 488 | 12.2 | 10.67 | 5 | 999 | 0 | 0 | Yes | 250 | 3 | ['laydown area', 'bearing capacity']
New Bedford | MA | North Atlantic | 30 | 366 | 9.1 | 9.1 | 20 | 999 | 1 | 1 | Yes | 200 | 3 | ['laydown area']
Port Everglades | FL | GOM | 2190 | 2000 | 11 | 12.5 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Galveston | TX | GOM | 840 | 10229 | 7.1 | 11 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Pascagoula | MS | GOM | 747 | 3857 | 11 | 9.4 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of New Orleans | LA | GOM | 460 | 3400 | 11 | 11 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Palm Beach | FL | GOM | 162 | 1981 | 9.4 | 9.4 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Gulf Port | MS | GOM | 160 | 1219 | 9.4 | 9.4 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Naval Weapons Station Earle Pier Complex, Belford | NJ | Central Atlantic | 200 | 215 | 13.7 | 10.67 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Werner Power Station | NJ | Central Atlantic | 90 | 250 | 7 | 7.62 | 0 | 999 | 1 | 0 | Yes | 250 | 3 | ['channel depth', 'bearing capacity']
South Brooklyn Marine Terminal | NY | Central Atlantic | 53 | 413 | 10.7 | 12.2 | 30 | 65.5 | 1 | 1 | Yes | 200 | 3 | ['laydown area']
Arthur Kill Terminal | NY | Central Atlantic | 32 | 396 | 10.67 | 10.67 | 29 | 999 | 1 | 0 | Yes | 200 | 3 | ['laydown area']

## Cable
Port | State | Region | Laydown area (acres) | Quayside length (m) | Berth depth (m) | Channel depth (m) | Bearing capacity (t/m2) | Air draft restriction (m) | State OSW goals | Existing commitments | Cable_decision | Cable_upgrade_cost | Cable_upgrade_time | Cable_fails
Port of Brunswick | GA | South Atlantic | 707 | 1876 | 10.5 | 10.5 | 0 | 62 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Sparrows Point / TradePoint Atlantic | MD | South Atlantic | 680 | 1020 | 11 | 11 | 0 | 999 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
Portsmouth Marine Terminal | VA | South Atlantic | 287 | 1079 | 13.1 | 13.1 | 0 | 999 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
General Cargo Terminal at Port of Wilmington | NC | South Atlantic | 284 | 2063 | 13 | 13 | 0 | 64 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Newport News Marine Terminal | VA | South Atlantic | 165 | 1060 | 12.2 | 12.2 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Columbus Terminal | SC | South Atlantic | 155 | 1066 | 13.7 | 13.7 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Lambert's Point, Norfolk | VA | South Atlantic | 110 | 517 | 14.6 | 12.2 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Quonset Business Park / Port of Davisville | RI | North Atlantic | 200 | 434 | 10.36 | 9.75 | 0 | 59.13 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
PG & E Facility, Bridgeport | CT | North Atlantic | 100 | 121.92 | 9.14 | 9 | 5.38 | 999 | 1 | 0 | Yes | 200 | 3 | ['quayside length', 'bearing capacity']
Searsport | ME | North Atlantic | 80 | 488 | 12.2 | 10.67 | 5 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Prov Port | RI | North Atlantic | 50 | 1097 | 9.1 | 12.2 | 0 | 59.13 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
New London State Pier | CT | North Atlantic | 45 | 1244 | 12.2 | 10.7 | 0 | 999 | 1 | 1 | Yes | 250 | 3 | ['laydown area', 'bearing capacity']
Salem | MA | North Atlantic | 42 | 484 | 9.75 | 9.75 | 0 | 999 | 1 | 1 | Yes | 250 | 3 | ['laydown area', 'bearing capacity']
South Quay | RI | North Atlantic | 35 | 457 | 10.36 | 12.2 | 0 | 59.13 | 0 | 0 | Yes | 250 | 3 | ['laydown area', 'bearing capacity']
New Bedford | MA | North Atlantic | 30 | 366 | 9.1 | 9.1 | 20 | 999 | 1 | 1 | Yes | 200 | 3 | ['laydown area']
Port Everglades | FL | GOM | 2190 | 2000 | 11 | 12.5 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Galveston | TX | GOM | 840 | 10229 | 7.1 | 11 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Pascagoula | MS | GOM | 747 | 3857 | 11 | 9.4 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of New Orleans | LA | GOM | 460 | 3400 | 11 | 11 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Palm Beach | FL | GOM | 162 | 1981 | 9.4 | 9.4 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Gulf Port | MS | GOM | 160 | 1219 | 9.4 | 9.4 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Tampa | FL | GOM | 100 | 1829 | 11 | 12.5 | 0 | 58.2 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Naval Weapons Station Earle Pier Complex, Belford | NJ | Central Atlantic | 200 | 215 | 13.7 | 10.67 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Paulsboro | NJ | Central Atlantic | 120 | 260 | 12.2 | 12.2 | 0 | 53 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
Werner Power Station | NJ | Central Atlantic | 90 | 250 | 7 | 7.62 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
South Brooklyn Marine Terminal | NY | Central Atlantic | 53 | 413 | 10.7 | 12.2 | 30 | 65.5 | 1 | 1 | Yes | 100 | 3 | []
Arthur Kill Terminal | NY | Central Atlantic | 32 | 396 | 10.67 | 10.67 | 29 | 999 | 1 | 0 | Yes | 200 | 3 | ['laydown area']

## Transition piece
Port | State | Region | Laydown area (acres) | Quayside length (m) | Berth depth (m) | Channel depth (m) | Bearing capacity (t/m2) | Air draft restriction (m) | State OSW goals | Existing commitments | Transition piece_decision | Transition piece_upgrade_cost | Transition piece_upgrade_time | Transition piece_fails
Port of Brunswick | GA | South Atlantic | 707 | 1876 | 10.5 | 10.5 | 0 | 62 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Sparrows Point / TradePoint Atlantic | MD | South Atlantic | 680 | 1020 | 11 | 11 | 0 | 999 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
Portsmouth Marine Terminal | VA | South Atlantic | 287 | 1079 | 13.1 | 13.1 | 0 | 999 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
General Cargo Terminal at Port of Wilmington | NC | South Atlantic | 284 | 2063 | 13 | 13 | 0 | 64 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Newport News Marine Terminal | VA | South Atlantic | 165 | 1060 | 12.2 | 12.2 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Columbus Terminal | SC | South Atlantic | 155 | 1066 | 13.7 | 13.7 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Lambert's Point, Norfolk | VA | South Atlantic | 110 | 517 | 14.6 | 12.2 | 0 | 999 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
Quonset Business Park / Port of Davisville | RI | North Atlantic | 200 | 434 | 10.36 | 9.75 | 0 | 59.13 | 0 | 0 | Yes | 300 | 3 | ['quayside length', 'channel depth', 'bearing capacity']
Searsport | ME | North Atlantic | 80 | 488 | 12.2 | 10.67 | 5 | 999 | 0 | 0 | Yes | 200 | 3 | ['quayside length', 'bearing capacity']
Mystic River, Everett | MA | North Atlantic | 80 | 380 | 11.5 | 12.2 | 0 | 41.15 | 1 | 0 | Yes | 200 | 3 | ['quayside length', 'bearing capacity']
Prov Port | RI | North Atlantic | 50 | 1097 | 9.1 | 12.2 | 0 | 59.13 | 0 | 0 | Yes | 250 | 3 | ['laydown area', 'bearing capacity']
New London State Pier | CT | North Atlantic | 45 | 1244 | 12.2 | 10.7 | 0 | 999 | 1 | 1 | Yes | 250 | 3 | ['laydown area', 'bearing capacity']
Salem | MA | North Atlantic | 42 | 484 | 9.75 | 9.75 | 0 | 999 | 1 | 1 | Yes | 400 | 3 | ['laydown area', 'quayside length', 'channel depth', 'bearing capacity']
Port Everglades | FL | GOM | 2190 | 2000 | 11 | 12.5 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Galveston | TX | GOM | 840 | 10229 | 7.1 | 11 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Pascagoula | MS | GOM | 747 | 3857 | 11 | 9.4 | 0 | 999 | 0 | 0 | Yes | 250 | 3 | ['channel depth', 'bearing capacity']
Port of New Orleans | LA | GOM | 460 | 3400 | 11 | 11 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Beaumont | TX | GOM | 206 | 2575 | 11 | 11 | 0 | 41.5 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Palm Beach | FL | GOM | 162 | 1981 | 9.4 | 9.4 | 0 | 999 | 0 | 0 | Yes | 250 | 3 | ['channel depth', 'bearing capacity']
Port of Gulf Port | MS | GOM | 160 | 1219 | 9.4 | 9.4 | 0 | 999 | 0 | 0 | Yes | 250 | 3 | ['channel depth', 'bearing capacity']
Port of Tampa | FL | GOM | 100 | 1829 | 11 | 12.5 | 0 | 58.2 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
New York Container Terminal | NY | Central Atlantic | 260 | 650 | 13.7 | 15.24 | 0 | 46.9 | 1 | 0 | Yes | 150 | 3 | ['bearing capacity']
South Brooklyn Marine Terminal | NY | Central Atlantic | 53 | 413 | 10.7 | 12.2 | 30 | 65.5 | 1 | 1 | Yes | 150 | 3 | ['quayside length']
Port of Coeymans Marine Terminal | NY | Central Atlantic | 50 | 1067 | 9.14 | 9.14 | 19.5 | 41 | 1 | 1 | Yes | 300 | 3 | ['laydown area', 'channel depth']
Arthur Kill Terminal | NY | Central Atlantic | 32 | 396 | 10.67 | 10.67 | 29 | 999 | 1 | 0 | Yes | 250 | 3 | ['laydown area', 'quayside length']

## Steel plate
Port | State | Region | Laydown area (acres) | Quayside length (m) | Berth depth (m) | Channel depth (m) | Bearing capacity (t/m2) | Air draft restriction (m) | State OSW goals | Existing commitments | Steel plate_decision | Steel plate_upgrade_cost | Steel plate_upgrade_time | Steel plate_fails
Port of Brunswick | GA | South Atlantic | 707 | 1876 | 10.5 | 10.5 | 0 | 62 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Sparrows Point / TradePoint Atlantic | MD | South Atlantic | 680 | 1020 | 11 | 11 | 0 | 999 | 1 | 1 | Yes | 150 | 3 | ['bearing capacity']
Portsmouth Marine Terminal | VA | South Atlantic | 287 | 1079 | 13.1 | 13.1 | 0 | 999 | 1 | 1 | Yes | 250 | 3 | ['laydown area', 'bearing capacity']
General Cargo Terminal at Port of Wilmington | NC | South Atlantic | 284 | 2063 | 13 | 13 | 0 | 64 | 1 | 0 | Yes | 250 | 3 | ['laydown area', 'bearing capacity']
Port Everglades | FL | GOM | 2190 | 2000 | 11 | 12.5 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Galveston | TX | GOM | 840 | 10229 | 7.1 | 11 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
Port of Pascagoula | MS | GOM | 747 | 3857 | 11 | 9.4 | 0 | 999 | 0 | 0 | Yes | 250 | 3 | ['channel depth', 'bearing capacity']
Port of New Orleans | LA | GOM | 460 | 3400 | 11 | 11 | 0 | 999 | 0 | 0 | Yes | 150 | 3 | ['bearing capacity']
New York Container Terminal | NY | Central Atlantic | 260 | 650 | 13.7 | 15.24 | 0 | 46.9 | 1 | 0 | Yes | 250 | 3 | ['laydown area', 'bearing capacity']
South Brooklyn Marine Terminal | NY | Central Atlantic | 53 | 413 | 10.7 | 12.2 | 30 | 65.5 | 1 | 1 | Yes | 250 | 3 | ['laydown area', 'quayside length']
Port of Coeymans Marine Terminal | NY | Central Atlantic | 50 | 1067 | 9.14 | 9.14 | 19.5 | 41 | 1 | 1 | Yes | 300 | 3 | ['laydown area', 'channel depth']
Arthur Kill Terminal | NY | Central Atlantic | 32 | 396 | 10.67 | 10.67 | 29 | 999 | 1 | 0 | Yes | 250 | 3 | ['laydown area', 'quayside length']